## Sheet1
Unique ID | User story | Assignee | Story Points | Depends on | Testing User Story? | Reviewers(Dev) | Reviewers(Master) | To be Implemented | To be Tested
CREATE
| As a registred User(Member/Partner) or an Unregistred User… I should be able to contact The Firm. (Lirten-Hub Admins "Contact Us Route") | Ibrahim |  |  |  | Hassan/Gasser
DELETE
READ
| As an Admin, I should be able to view all Partners. | Abdelrahman |  |  |  | Hassan/Gasser/Ibrahim
| As an Admin, I should be able to view all Members. | Abdelrahman |  |  |  | Hassan/Gasser/Ibrahim
| As an Admin, I should be able to see All expired Members. | Nada |  |  |  | Hassan/Gasser/Ibrahim
| As an Admin, I should be able to view all expired Partners. | Nada |  |  |  | Hassan/Gasser/Ibrahim
UPDATE
| As a Partner, I should be able to Hire an applicant. | Ahmed Salah
| Postponed to next Sprints |  |  |  |  | Hassan/Gasser/Ibrahim
Frontend
| As a Member I should be able to Sign-Up. (Create Member Form). | Manar |  |  |  | Hassan/Gasser/Ibrahim
| As a Partner I should be able to Sign-Up. (Create Partner Form). (Remaking the Component) | Manar |  |  |  | Hassan/Gasser/Ibrahim
| As a registred User (Member/ Partner/ Admin) I should be able to view my Notifications. (2 Components"One for Notification Element, and Another for Notification Page to view the element.") | Islam |  |  |  | Hassan/Gasser/Ibrahim
| As a Partner, I should be able to Hire an applicant. | Gasser |  |  |  | Hassan/Ibrahim
| As a Partner, I should be able to give feedback about one of my employees. | Gasser |  |  |  | Hassan/Ibrahim
| As a member, I should be able to give feedback about a Partner that I have an experience with. (Worked for, or currently working for). | Gasser |  |  |  | Hassan/Ibrahim
| As a User (Member/ Partner) I should be able to Sign-In with my e-mail and password. (Rest of Authentication). | Ahmed Hassan |  |  |  | Gasser/Ibrahim
| As a Partner/Admin I should be able to create an Event. (a Button that redirects to Create Event Page) | Esraa |  |  |  | Hassan/Gasser/Ibrahim
| As a Partner I should be able to create a Vacancy. (a Button that redirects to Create Vacancy Page) | Esraa |  |  |  | Hassan/Gasser/Ibrahim
| As a Partner/Member I should be able to view the feedbacks written for me through my Profile. | Mohamed Sabry |  |  |  | Hassan/Gasser/Ibrahim
| The system should be able to track the validity of the created events. | Ibrahim |  |  |  | Hassan/Gasser
Adjustments/Enhancements
Lirten-Hub Identity Integration.
Adjustments to UI and UX.
Models Adjustments (Removal of some things that make no sense in some entities)
Routes adjustments ()
Payment Method for Attending the Events (Stripe)