## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
CREATE
1 | As a member I can register/create my profile | 5 | Ahmed Salah
2 | As a partner I can register/create my profile | 5 | Ahmed Salah
3 | As a partner I can submit a request to create an event | 5 | Manar
4 | As a admin I can create an event directly | 5 | Manar
5 | As a partner I can submit a vacancy announcement request | 5 | Nada
6 | As a partner/admin I can add comments on my negotiation posts of events | 5 | Nada
7 | As a partner/admin I can add comments on my negotiation posts of vacancies | 5 | Ibrahim
8 | As a partner can give a feedback on a member who worked for me | 5 | Mohamed Sabri
9 | As a member can give a feedback on a partner i worked with | 5 | Gasser
DELETE
10 | As a partner I can delete my event request before it's approved | 1 | Abdelrahman | 6
11 | As a partner I can delete my vacancy request before it's approved | 1 | Abdelrahman | 7
READ
12 | As a admin/member/partner, I can view my/others'(members/partners) profiles | 3 | Ibrahim | 3 and 4
13 | As a partner/member/admin I can view my own notifications | 3 | Islam | 10
14 | As a partner/member/admin I can view approved events | 3 | Islam | 6
15.1 | As an admin I can negotiate (add comment) to an event request post with the partner | 3 | Hassan | 6
15.2 | As a partner I can negotiate (add comment) to an event request post with the admin | 3 | Hassan | 6
15.3 | As an admin I can negotiate (add comment) to a vacancy announcement request post with the partner | 3 | Hassan | 7
15.4 | As a partner I can negotiate (add comment) to a vacancy announcement request post with the admin | 3 | Hassan | 7
16 | As a partner I can view members who applied to my (approved ONLY) vacancies | 3 | Ibrahim
17 | As an admin I can view pending vacancies announcements requests | 3 | Abdelrahman | 7
18 | As an admin I can view pending events' requests | 3 | Manar | 6
UPDATE
19.1 | As a member I can update my profile (Address, Name, Password, Skills, Interests) | 4 | Mohamed Sabri | 3
19.2 | As an admin I can update members' (Membership Expiry Date, Member State). | 4 | Mohamed Sabri | 3
20 | As a partner I can update my profile (Board Members, Pending vacancies, Password, Pending events). | 4 | Gasser | 4
21 | As a partner I can update my pending events (Date, Location, Description, Price, Type, Topics, Speakers, Number of Attendees, Remaining Places). | 4 | Gasser | 6
22 | As a partner I can update my pending vacancies (Duration, Location, Description, Salary, Daily hours) | 4 | Islam | 7
23 | As an admin I can change a Vacancy's (REQUEST) Status from submitted to approved | 4 | Esraa | 7
24 | As a partner I can change my Vacancy's (APPROVED) Status from approved to closed | 4 | Esraa
25 | As an admin I can update my profile (Name, Password) | 4 | Esraa | 3