## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | Reviewers(Dev) | Reviewers(Master) | To be Implemented | To be Tested
CREATE
3 | As a partner I can submit a request to create an event | 5 | Manar |  |  | Esraa
4 | As a admin I can create an event directly | 5 | Manar |  |  | Esraa
5 | As a partner I can submit a vacancy announcement request | 5 | Nada |  |  | Hassan
6 | As a partner/admin I can add comments on my negotiation posts of events | 5 | Nada |  |  | Hassan
DELETE
10 | As a partner I can delete my event request before it's approved | 1 | Abdelrahman | 6 |  | Gasser
11 | As a partner I can delete my vacancy request before it's approved | 1 | Abdelrahman | 7 |  | Gasser
READ
14 | As a partner/member/admin I can view approved events | 3 | Islam | 6
15.1 | As an admin I can negotiate (read comment) to an event request post with the partner | 3 | Hassan | 6 |  | Ibrahim
15.2 | As a partner I can negotiate (read comment) to an event request post with the admin | 3 | Hassan | 6 |  | Ibrahim
15.3 | As an admin I can negotiate (read comment) to a vacancy announcement request post with the partner | 3 | Hassan | 7 |  | Ibrahim
15.4 | As a partner I can negotiate (read comment) to a vacancy announcement request post with the admin | 3 | Hassan | 7 |  | Ibrahim
17 | As an admin I can view pending vacancies announcements requests | 3 | Abdelrahman | 7 |  | Gasser
18 | As an admin I can view pending events' requests | 3 | Manar | 6 |  | Esraa
19 | As a Partner, I can view All My Pending(yet not approved) Vacancy Announcement Requests. (READ) | 3 | Ahmed Salah | 5 |  | Sabri, Abdelrahman
20 | As a Partner, I can view All My Pending(yet not approved) Event Requests. (READ) | 3 | Ahmed Salah | 4 |  | Sabri, Abdelrahman
21.1 | As a Partner, I can view an Event Post. (READ) | 3 | Mohamed Sabri | 4 |  | Gasser, Nada
21.2 | As a Partner, I can view a Vacancy Post. (READ) | 3 | Mohamed Sabri | 5 |  | Gasser, Nada
22.1 | As a member I can view recommended events that match my (Past attended Events, Location, Interests) (READ) | 3 | Ibrahim | 4 |  | Hassan, Manar
22.2 | As a member I can view recommended vacancies that match my (Skills, Locations, Availability) (READ) | 3 | Ibrahim | 5 |  | Hassan, Manar
UPDATE
28 | As an admin I can change a Vacancy's (REQUEST) Status from submitted to approved | 4 | Esraa | 7 |  | Manar
29 | As a partner I can change my Vacancy's (APPROVED) Status from approved to closed | 4 | Esraa |  |  | Manar
30 | As an admin I can update my profile (Name, Password) | 4 | Esraa | 3 |  | Manar
Postponed to next Sprints
31 | As a user(member/admin/partner) I can change my password.
32.1 | As a member i can register to an event (Add to Event Attendees). (UPDATE)
32.2 | As a member i should be able to attend an event. (Change the event). (UPDATE)
33 | As a system i should be able to hash Passwords and save them. (UPDATE)
34 | As a member/partner/admin i should be sent an E-mail with a new Password in case i forget mine.