## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | Reviewers(Dev) | Reviewers(Master) | To be Implemented | To be Tested
CREATE
5 | As a partner I can submit a vacancy announcement request | 5 | Nada |  |  | Hassan
6 | As a partner/admin I can add comments on my negotiation posts of events | 5 | Nada |  |  | Hassan
DELETE
10 | As a partner I can delete my event request before it's approved | 1 | Abdelrahman | 6 |  | Gasser
11 | As a partner I can delete my vacancy request before it's approved | 1 | Abdelrahman | 7 |  | Gasser
READ
17 | As an admin I can view pending vacancies announcements requests | 3 | Abdelrahman | 7 |  | Gasser
UPDATE
31 | Postponed to next Sprints
32.1 | As a user(member/admin/partner) I can change my password.
32.2 | As a member i can register to an event (Add to Event Attendees). (UPDATE)
33 | As a member i should be able to attend an event. (Change the event). (UPDATE)
34 | As a system i should be able to hash Passwords and save them. (UPDATE)
35 | As a member/partner/admin i should be sent an E-mail with a new Password in case i forget mine.