## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
CREATE
1 | As a member I can register/create my profile | 5 | Ahmed Salah
2 | As a partner I can register/create my profile | 5 | Ahmed Salah
3 | As a partner I can submit a request to create an event | 5 | Manar
4 | As a admin I can create an event directly | 5 | Manar
5 | As a partner I can submit a vacancy announcement request | 5 | Nada
6 | As a partner/admin I can add comments on my negotiation posts of events | 5 | Nada
7 | As a partner/admin I can add comments on my negotiation posts of vacancies | 5 | Ibrahim
8 | As a partner can give a feedback on a member who worked for me | 5 | Mohamed Sabri
9 | As a member can give a feedback on a partner i worked with | 5 | Gasser
DELETE
10 | As a partner I can delete my event request before it's approved | 1 | Abdelrahman | 6
11 | As a partner I can delete my vacancy request before it's approved | 1 | Abdelrahman | 7
READ
12 | As a admin/member/partner, I can view my/others'(members/partners) profiles | 3 | Ibrahim | 3 and 4
13 | As a partner/member/admin I can view my own notifications | 3 | Islam | 10
14 | As a partner/member/admin I can view approved events | 3 | Islam | 6
15.1 | As an admin I can negotiate (read comment) to an event request post with the partner | 3 | Hassan | 6
15.2 | As a partner I can negotiate (read comment) to an event request post with the admin | 3 | Hassan | 6
15.3 | As an admin I can negotiate (read comment) to a vacancy announcement request post with the partner | 3 | Hassan | 7
15.4 | As a partner I can negotiate (read comment) to a vacancy announcement request post with the admin | 3 | Hassan | 7
16 | As a partner I can view members who applied to my (approved ONLY) vacancies | 3 | Ibrahim
17 | As an admin I can view pending vacancies announcements requests | 3 | Abdelrahman | 7
18 | As an admin I can view pending events' requests | 3 | Manar | 6
UPDATE
19.1 | As a member I can update my profile (Address, Name, Password, Skills, Interests) | 4 | Mohamed Sabri | 3
19.2 | As an admin I can update members' (Membership Expiry Date, Member State). | 4 | Mohamed Sabri | 3
20 | As a partner I can update my profile (Board Members, Pending vacancies, Password, Pending events). | 4 | Gasser | 4
21 | As a partner I can update my pending events (Date, Location, Description, Price, Type, Topics, Speakers, Number of Attendees, Remaining Places). | 4 | Gasser | 6
22 | As a partner I can update my pending vacancies (Duration, Location, Description, Salary, Daily hours) | 4 | Islam | 7
23 | As an admin I can change a Vacancy's (REQUEST) Status from submitted to approved | 4 | Esraa | 7
24 | As a partner I can change my Vacancy's (APPROVED) Status from approved to closed | 4 | Esraa
25 | As an admin I can update my profile (Name, Password) | 4 | Esraa | 3
Postponed to next Sprint
26 | As a Partner, I can view All My Pending(yet not approved) Vacancy Announcement Requests. (READ)
27 | As a Partner, I can view All My Pending(yet not approved) Event Requests. (READ)
28 | As a Partner, I can view an Event Post. (READ)
29 | As a Partner, I can view a Vacancy Post. (READ)

## Sheet2
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
CREATE
1 | As a member I can register/create my profile | 5 | Ahmed Salah
2 | As a partner I can register/create my profile | 5 | Ahmed Salah
3 | As a partner I can submit a request to create an event | 5 | Manar
4 | As a admin I can create an event directly | 5 | Manar
5 | As a partner I can submit a vacancy announcement request | 5 | Nada
6 | As a partner/admin I can add comments on my negotiation posts of events | 5 | Nada
7 | As a partner/admin I can add comments on my negotiation posts of vacancies | 5 | Ibrahim
8 | As a partner can give a feedback on a member who worked for me | 5 | Mohamed Sabri
9 | As a member can give a feedback on a partner i worked with | 5 | Gasser
DELETE
10 | As a partner I can delete my event request before it's approved | 1 | Abdelrahman | 6
11 | As a partner I can delete my vacancy request before it's approved | 1 | Abdelrahman | 7
READ
12 | As a admin/member/partner, I can view my/others'(members/partners) profiles | 3 | Ibrahim | 3 and 4
13 | As a partner/member/admin I can view my own notifications | 3 | Islam | 10
14 | As a partner/member/admin I can view approved events | 3 | Islam | 6
15 | As an admin I can negotiate (read comment) to an event request post with the partner | 3 | Hassan | 6
16 | As a partner I can negotiate (read comment) to an event request post with the admin | 3 | Hassan | 6
17 | As an admin I can negotiate (read comment) to a vacancy announcement request post with the partner | 3 | Hassan | 7
18 | As a partner I can negotiate (read comment) to a vacancy announcement request post with the admin | 3 | Hassan | 7
19 | As a partner I can view members who applied to my (approved ONLY) vacancies | 3 | Ibrahim
20 | As an admin I can view pending vacancies announcements requests | 3 | Abdelrahman | 7
21 | As an admin I can view pending events' requests | 3 | Manar | 6
22 | As a Partner, I can view All My Pending(yet not approved) Vacancy Announcement Requests. (READ) | 3 | Ahmed Salah | 5 |  | Sabri, Abdelrahman
23 | As a Partner, I can view All My Pending(yet not approved) Event Requests. (READ) | 3 | Ahmed Salah | 4 |  | Sabri, Abdelrahman
24 | As a Partner, I can view an Event Post. (READ) | 3 | Mohamed Sabri | 4 |  | Gasser, Nada
25 | As a Partner, I can view a Vacancy Post. (READ) | 3 | Mohamed Sabri | 5 |  | Gasser, Nada
26 | As a member I can view recommended events that match my (Past attended Events, Location, Interests) (READ) | 3 | Ibrahim | 4 |  | Hassan, Manar
27 | As a member I can view recommended vacancies that match my (Skills, Locations, Availability) (READ) | 3 | Ibrahim | 5 |  | Hassan, Manar
28 | As a Partner, I can view All My Pending(yet not approved) Vacancy Announcement Requests. (READ) |  | Ahmed Salah
29 | As a Partner, I can view an Event Post. (READ) |  | Mohamed Sabri
30 | As a Partner, I can view a Vacancy Post. (READ) |  | Mohamed Sabri
31 | As a Partner, I can view All My Pending(yet not approved) Event Requests. (READ)
32 | As a member i can register to an event (Add to Event Attendees). (UPDATE) |  | Gasser
33 | As an Admin, I should be able to view all Partners. |  | Abdelrahman |  |  | Hassan/Gasser/Ibrahim
34 | As an Admin, I should be able to view all Members. |  | Abdelrahman |  |  | Hassan/Gasser/Ibrahim
35 | As an Admin, I should be able to see All expired Members. |  | Nada |  |  | Hassan/Gasser/Ibrahim
36 | As an Admin, I should be able to view all expired Partners. |  | Nada |  |  | Hassan/Gasser/Ibrahim
UPDATE
23.1 | As a member I can update my profile (Address, Name, Password, Skills, Interests) | 4 | Mohamed Sabri | 3
23.2 | As an admin I can update members' (Membership Expiry Date, Member State). | 4 | Mohamed Sabri | 3
24 | As a partner I can update my profile (Board Members, Pending vacancies, Password, Pending events). | 4 | Gasser | 4
25 | As a partner I can update my pending events (Date, Location, Description, Price, Type, Topics, Speakers, Number of Attendees, Remaining Places). | 4 | Gasser | 6
26 | As a partner I can update my pending vacancies (Duration, Location, Description, Salary, Daily hours) | 4 | Islam | 7
27 | As an admin I can change a Vacancy's (REQUEST) Status from submitted to approved | 4 | Esraa | 7
28 | As a partner I can change my Vacancy's (APPROVED) Status from approved to closed | 4 | Esraa
29 | As an admin I can update my profile (Name, Password) | 4 | Esraa | 3
30 | As a member, I can apply for a vacancy | 4 | Ibrahim Mohamed | 1,2,5 |  | Hassan, Manar | Hassan, Gasser, Ibrahim
31 | As a member i should be able to attend an event. (Change the event). (UPDATE) |  | Gasser
32 | As a user(member/admin/partner) I can change my password.
33 | As a Partner, I should be able to Hire an applicant. |  | Ahmed Salah
Postponed to next Sprint
36 | As a system i should be able to hash Passwords and save them. (UPDATE)
37 | As a member/partner/admin i should be sent an E-mail with a new Password in case i forget mine.
Frontend
1 | As a member/partner/admin I should be able to sign in. |  | Ahmed Hassan
2 | As an unregistered user I should be able to sign up. |  | Ahmed Hassan
3 | As a member/partner I can show my profile. |  | Manar Hatem
4 | As a member/partner I can edit my profile. |  | Manar Hatem
5 | As a partner I should be able to view all my events(sorted by status). |  | Manar Hatem
6 | As a member/partner/admin I should be able to view all vacancies. |  | Esraa Saad
7 | As a member or partner I should be able to view recommended vacancies. |  | Esraa Saad
8 | As an admin I should be able to view pending vacancies. |  | Esraa Saad
9 | As a partner I should be able to view all vacancies (sorted by status). |  | Esraa Saad
10 | As a admin/partner I should be able to comment on an event. |  | Abdulreheman
11 | As a partner I should be able to delete all/one of my pending events. |  | Abdulreheman
12 | As a admin/partner I should be able to comment on an vacancy. |  | Nada
13 | As a partner I should be able to delete all/one of my pending vacancies. |  | Nada
14 | As a user I should receive notifications. |  | Islam Omar
15 | As a member I should be able to reserve a seat in an event. |  | Gasser Khaled
16 | As a member I should be able to unreserve a seat in an event. |  | Gasser Khaled
17 | As a member I should be able to apply for a vacancy. |  | Gasser Khaled
18 | As an admin I should be able to edit my password. |  | Ahmed Salah
19 | As an admin I should be able to approve pending events/vacancies. |  | Mohamed Sabri
20 | As a partner I should be able to edit my pending events. |  | Mohamed Sabri
21 | As a partner I should be able to open my approved event. |  | Ibrahim Mohamed
22 | As a partner I should be able to close my approved event. |  | Ibrahim Mohamed
23 | As a partner I should be able to open my approved vacancy. |  | Ibrahim Mohamed
24 | As a partner I should be able to close my approved vacancy. |  | Ibrahim Mohamed
25 | Navigation bar. |  | Ibrahim Mohamed
26 | Homepage(About/Landing Page). |  | Ibrahim Mohamed
27 | As a Member I should be able to Sign-Up. (Create Member Form). |  | Manar |  |  | Hassan/Gasser/Ibrahim
28 | As a Partner I should be able to Sign-Up. (Create Partner Form). (Remaking the Component) |  | Manar |  |  | Hassan/Gasser/Ibrahim
29 | As a registred User (Member/ Partner/ Admin) I should be able to view my Notifications. (2 Components"One for Notification Element, and Another for Notification Page to view the element.") |  | Islam |  |  | Hassan/Gasser/Ibrahim
30 | As a Partner, I should be able to Hire an applicant. |  | Gasser |  |  | Hassan/Ibrahim
31 | As a Partner, I should be able to give feedback about one of my employees. |  | Gasser |  |  | Hassan/Ibrahim
32 | As a member, I should be able to give feedback about a Partner that I have an experience with. (Worked for, or currently working for). |  | Gasser |  |  | Hassan/Ibrahim
33 | As a User (Member/ Partner) I should be able to Sign-In with my e-mail and password. (Rest of Authentication). |  | Ahmed Hassan |  |  | Gasser/Ibrahim
34 | As a Partner/Admin I should be able to create an Event. (a Button that redirects to Create Event Page) |  | Esraa |  |  | Hassan/Gasser/Ibrahim
35 | As a Partner I should be able to create a Vacancy. (a Button that redirects to Create Vacancy Page) |  | Esraa |  |  | Hassan/Gasser/Ibrahim
36 | As a Partner/Member I should be able to view the feedbacks written for me through my Profile. |  | Mohamed Sabry |  |  | Hassan/Gasser/Ibrahim
37 | The system should be able to track the validity of the created events. |  | Ibrahim |  |  | Hassan/Gasser
Adjustments/Enhancements
1 | Lirten-Hub Identity Integration.
2 | Adjustments to UI and UX.
3 | Models Adjustments (Removal of some things that make no sense in some entities)
4 | Routes adjustments ()
5 | Payment Method for Attending the Events (Stripe)