## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | Reviewers(Dev) | Reviewers(Master)
CREATE
5 | As a partner I can submit a vacancy announcement request |  | Nada |  |  | Ahmed Hassan, Abdelrahman
2 | As a member I can register/create my profile |  | Ahmed Salah |  |  | Gasser, Ibrahim, Ahmed Hassan, Manar
DELETE
READ
16 | As a partner I can view members who applied to my (approved ONLY) vacancies |  | Ahmed Hassan |  |  | Gasser, Ibrahim, Manar
17 | As an admin I can view pending vacancies announcements requests |  | Abdelrahman |  |  | Ahmed Hassan, Nada
| As a member I can view recommended events that match my (Past attended Events, Location, Interests) (READ) |  | Ibrahim |  |  | Gasser, Ahmed Hassan, Manar
18 | As an admin I can view pending events' requests |  | Manar |  |  | Gasser, Ibrahim, Ahmed Hassan
14 | As a partner /user /admin i can display event post |  | Sabry |  |  | Gasser, Ibrahim, Ahmed Hassan, Manar
13 | As a partner/admin/member i can view my own notifications |  | Islam |  |  | Ibrahim, Ahmed Hassan, Manar
UPDATE
19.1 | As an admin I can update my profile (Name, Password) |  | Esraa |  |  | Gasser, Ibrahim, Ahmed Hassan, Manar
9 | As a member can give a feedback on a partner i worked with |  | Gasser |  |  | Ibrahim, Ahmed Hassan, Manar
Postponed to next Sprints
32.1 | As a user(member/admin/partner) I can change my password.
32.2 | As a member i can register to an event (Add to Event Attendees). (UPDATE)
33 | As a member i should be able to attend an event. (Change the event). (UPDATE)
34 | As a system i should be able to hash Passwords and save them. (UPDATE)
35 | As a member/partner/admin i should be sent an E-mail with a new Password in case i forget mine.